## Slide 1: Example Release Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Fishy Fish
Release x Kick-Off
New Features Developed
Stabilize
Patch Updates
App Development
Release (x+1) Kick-Off
RC1
RC2
RC3
Final Release (x)
x.0.1
x.0.2
x.0.3
x.0.4

## Slide 2: Release Candidates
RC1
RC3
RC2
Core Feature Freeze
Platform Freeze
Core APIs Frozen (App FW, Public Services, GUI Toolkit)
SDK available for App Developers on at least 1 Reference Board
Final RC
Reference Applications Frozen
Documentation Complete
SDK for All Reference Boards
Final
Release
BSPs Frozen
Release Branch Created
All source code frozen (SRCREV pinned)
Test Cases Frozen

## Slide 3: 2017 AGL Schedule
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Charming Chinook
3.0.0
3.0.2
3.0.1
3.0.3
3.0.4
3.0.5
Daring Dab
Feature Development
Electric Eel
RC1
RC3
5.0.0
RC2
Feature Development
As of 25 July 2017
RC1
RC3
4.0.0
4.0.3
4.0.1
4.0.2
4.0.4
RC2

## Slide 4: Daring Dab
Mar | Apr | May | Jun | Jul | Aug
Daring Dab
New Features Developed
Stabilize
Patch Updates
App Development
RC1
5.31
RC2
7.05
Final Release 7.28
RC3
7.21
4.0.1

## Slide 5: Electric Eel
Jul | Aug | Sep | Oct | Nov | Dec | Jan
Electric Eel
New Features Developed
Stabilize
Patch Updates
App Development
RC1
9.30
RC2
10.30
Final Release 12.15
RC3
11.30
5.0.1
CES 2018
0
Start of Development
7.10

## Slide 6: Funky Flounder
Jan | Apr | May | Jun | Jul | Aug
Funky Flounder
New Features Developed
Stabilize
Patch Updates
App Development
RC1
6.01
RC2
6.22
Final Release 7.20
RC3
7.06
6.0.1
Start of Development
1.15